## Slide 1
February 2015
An introduction to the switch from trivalent to bivalent oral polio vaccines

## Slide 2: Contents
Rationale for OPV withdrawal
Timelines for switching from tOPV to bOPV
Programmatic implications of the switch

## Slide 3: Children paralyzed by polio
Chart: Polio cases (thousands)
| 1985 | 1986 | 1987 | 1988 | 1989 | 1990 | 1991 | 1992 | 1993 | 1994 | 1995 | 1996 | 1997 | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012
Estimated | 387 | 323 | 394 | 345 | 261 | 233 | 134 | 137 | 76 | 73 | 60 | 33 | 18 | 10 | 10 | 0.719 | 0.483 | 1.918 | 0.784 | 1.255 | 1.979 | 1.997 | 1.315 | 1.651 | 1.604 | 1.352 | 0.65 | 0.22
Type 2 polio eradicated (WPV)

## Slide 4: Vaccine-derived polio outbreaks (circulating VDPVs) 2000-2013
Type 2 (478 cases)
Type 1 (79 cases)
Type 3 (9 cases)
Type 2
Type 1
Type 3

## Slide 5: World Health Assembly resolution 65.5
“Declares polio eradication a programmatic emergency for global public health...
…“urges the Director General to rapidly finalize a polio endgame plan…
“…and inform Member States of the potential timing of a switch from trivalent to bivalent OPV for all routine immunization programmes”
(May 2012)

## Slide 6: Coming dates for the Endgame Plan
May 2015 | World Health Assembly to consider resolution on the switch
December 2015 | At least 1 dose of IPV introduced into routine immunization programmes in all countries
April 2016 | Withdraw type 2 OPV globally
2020? | After all wild polioviruses have been fully eradicated, withdraw all OPVs

## Slide 7: Rationale for switching from trivalent OPV to bivalent OPV
Currently, the risks associated with the type 2 component of tOPV outweigh the benefits
Since 1999, type 2 wild poliovirus has not been detected
The type 2 component of tOPV:
  Causes more than 90% of vaccine-derived polio viruses (VDPVs)
  Causes approx. 40% of vaccine-associated paralytic polio (VAPP) cases
  Interferes with the immune response to poliovirus types 1 and 3 in tOPV
IPV introduction will help to:
  Reduce risks associated with the withdrawal of OPV type 2
  Facilitate interruption of transmission with the use of monovalent OPV type 2 in the case of outbreaks
  Hasten eradication by boosting immunity to poliovirus types 1 and 3

## Slide 8: Contents
Rationale for OPV withdrawal
Timelines for switching from tOPV to bOPV
Programmatic implications of the switch

## Slide 9: Milestones towards the switch
May 2015, World Health Assembly (WHA):
Discussion on progress and timelines towards OPV2 withdrawal in April 2016
As proposed by the WHO Executive Board in January 2015, the WHA may consider a resolution calling on member states to implement the switch
  October 2015, Strategic Advisory Group of Experts (SAGE):
  SAGE will review and decide on final risk assessment data to determine if the trigger for OPV2 withdrawal has been met
  Trigger for OPV2 withdrawal: global absence of cVDPV2s that are known to have been circulating for more than 6 months ("persistent" cVDPV2s)
  If SAGE confirms that the trigger has been met, GPEI will announce the 2016 switch dates
  Once the decision to proceed with the switch in 2016 is announced, it is irrevocable. The switch will not be postponed after that date
  However, if the trigger condition is not met in September 2015, the switch will be reassessed and may be postponed until 2017

## Slide 10: General steps for the switch
Readiness criteria
IPV is introduced in all countries by end 2015
Absence of all ‘persistent’ cVDPV2s globally
Synchronized switch
WPV2 global eradication is verified
Replace tOPV with bOPV globally in a 2-week span
Phase 1 containment activities are completed, with appropriate handling of residual type 2 materials
bOPV is licensed for routine immunization
Surveillance and response capacity are implemented for WPV2 detection, and a type 2 monovalent OPV stockpile set up
No use of tOPV after this period
Trigger
World Health Assembly in May to consider:
SAGE in October to consider:

## Slide 11: Switch window example: April 2016 in a country
week 1 week 2
week 3
week 4
Global Validation Day
Global switch
2-week window
The country selects a ‘National Switch Day’ from this window
Global validation 2-week window
e.g. National
Switch Day:
stop tOPV use
e.g. National Validation Day:
all tOPV disposed
disposal and validation
2-week window

## Slide 12: Global synchronization and planning
To minimize the risk of any type 2 cVDPV re-emergence or outbreaks from the use of tOPV, the switch will need to take place everywhere worldwide within a 2-week period.
  Implications for tOPV supply planning:
  tOPV stocks needed for national routine immunization only until March 2016
  Countries should coordinate with their relevant supplier to plan around the switch
  The last in-country distribution of tOPV should take place 4 weeks before the switch date
  Important to avoid tOPV stock-outs in the weeks before the switch
  Countries should enhance stock monitoring and management capacity starting in 2015
  Implications for bOPV:
  3-6 months of supplies of bOPV should be planned for and received in countries from January 2016 onwards
  New bOPV stocks should be kept at central level, stored separately until distribution
  Supply may be distributed to vaccination points starting 2 weeks before the national switch date
Countries should not switch before the global switch window.

## Slide 13: Contents
Rationale for OPV withdrawal
Timelines for switching from tOPV to bOPV
Programmatic implications of the switch

## Slide 14: Mitigating risks before the switch
High population immunity is necessary for successful OPV cessation, to help reduce the risks of cVDPV emergence
Higher risk countries will conduct tOPV SIAs in Q4 2015 and Q1 2016, at national and/or subnational level
  The plan for risk mitigation SIAs was discussed and agreed by SAGE in October 2014.

## Slide 15
Requires a complete global replacement of tOPV by bOPV
Overall process steps: switch  recall  dispose  validate
  Switch: tOPV is removed from the (private and public sector) cold chain and replaced with bOPV on the National Switch Date
  Recall: tOPV is transported to collection points
  Dispose: tOPV stocks are safely disposed
  Validate: national and international monitors supervise the process and validate the complete absence of tOPV stock on National Validation Day (2 weeks after National Switch Date)
Manufacturers will not supply any more tOPV starting a short period before the switch.
Principles of tOPV withdrawal

## Slide 16: Country level considerations
Planning and management
Now: Forecast quantities for supply and procurement of bOPV and tOPV
Coordinate with national committees and private sector, for both routine immunization and supplemental campaigns
Develop a national operational plan by mid 2015
Regulatory
Initiate process for national licensure of bOPV licensure (in countries that require it)
Note that bOPV is the same as tOPV for volume, heat sensitivity, VVM, and wastage
Implementation, monitoring, logistics, communication
Establish a ‘switch support team’ to implement the plan
Adapt workplans, communication and training materials to local context and language
Update data tools
Update information systems to monitor activities at all levels

## Slide 17: Preparation underway at a global level
Involving vaccine manufacturers and national regulatory authorities on bOPV licensure and supply. Consulting on presentations and labelling
Developing procurement and distribution strategies to minimize stocks of tOPV while avoiding stockouts prior to the switch date, including with self-procuring countries
Developing and disseminating Switch protocol templates, workplans, communication and training materials
Seeking endorsement of the switch by WHO member states through an expected World Health Assembly discussion in May 2015
Establishing monitoring systems at all levels to track progress

## Slide 18: Next steps for switch planning and communications
Switch implementation working group (under the IMG)
Coordinating planning, preparations, and technical assistance.
Communications and training
Disseminating information and hosting webinars from Q1 2015 to inform planning and developing materials for health worker training
The Switch Protocol: an implementation guide
The Protocol will be published in early 2015
Regional briefings/trainings will help build awareness and capacity
Liaison with UNICEF country offices and relevant manufacturers for self-procuring countries vital to implementation and supply strategies
Countries will be responsible for monitoring stock levels and adjusting the frequency and/or quantities of tOPV deliveries to minimize risk of excess stocks and stock-outs at country level.
Country pilot exercises will help refine preparations, guidance, and information collection systems

## Slide 19
COMING SOON!
OPV technical background, communications and training materials:
http://www.who.int/immunization/diseases/poliomyelitis/endgame_objective2/en/

## Slide 20: THANK YOU
For more information:
http://www.who.int/immunization/diseases/poliomyelitis/endgame_objective2/en/